## Slide 1
High Street & School Road, Godshill
Carriageway Reconstruction and Resurfacing

## Slide 2: Road Condition

## Slide 3: Scope of Works
Various dig depths of 80mm, 100mm & 240mm

## Slide 4: Challenges
Access
School – half term (19 – 30 October)
Businesses – including trade during half term & Halloween
Residents
Parking
Pedestrian safety - sections without footways
Traffic - through traffic & rat running

## Slide 5: Challenges
Delivery
Adverse weather
Low temperatures - laying & compacting materials
Reduced daylight hours
Location of defects
Depth of excavations – up to 240mm deep
Safety of road users and our staff during works
Unmapped underground services

## Slide 6: Challenges
Timing
Months | Challenges
April – August | Peak tourism period but ideal conditions for highway works
September | Late tourism period
October | Half term holidays
November – mid December | Tourism businesses close until Easter
21st December – 3rd January | Christmas holidays
Jan, Feb, early March | Increased risk of lost shifts due to poor weather & low temperatures
26th March | Good Friday

## Slide 7: Two Stages
STAGE | WORK | WHEN
1 | Reconstruction Localised deep repairs | Autumn / Winter 2026
2 | Resurfacing Whole road resurfacing | Spring 2027 (nights)

## Slide 8: STAGE 1 : Reconstruction
Change of dates following visits to businesses
Revised dates - 2nd November - 15th January
Road space - until 29th January if required
Pause - 11th December – 4th January for Christmas trade
24 hour closure – 3 phases
Open weekends where possible
Event - “Christmas Cracker” on Saturday 5th December

## Slide 9: Phases
3 Phases

## Slide 10: Phases
East of West Street to west of School Crescent
Phase 1

## Slide 11: Phases
East of School Crescent to Church Hollow (inc junction)
Phase 2

## Slide 12: Phases
South of Church Hollow to approx 100 metres east of Hollow Lane.
Phase 3

## Slide 13: Signed Diversion Route

## Slide 14: STAGE 2 - Resurfacing
Plane and resurface entire road
Likely April 2027
Approx 4 -5 nights (19:30 – 07:00)
Reopen during the day (temporary surface)

## Slide 15: Communications
Businesses
Letters to residents
Press releases
Email bulletins
Website FAQs
Signage
Use of ‘X’ (formerly Twitter)

## Slide 16: QUESTIONS